## H2 2026 Candidates - Self Servi
Item name | Item description | Area | Priority | MW Effort | Rational | Predicted Impact | Owner | Link | Top line metric | Team Metric | Measurements | Dependencies in other domains | Category | Risk/Challenges | Effort Breakdown | PA | Committed
AHA - CLM delta | AHA solution for cases without compliance wave ( new licenses) where delta kYCshould be collected and sign relevant T&C - 8 M/W | Compliance | P0 | 8 | Prevent non compliant traffic before starting migration | Need to understand AHA traffic from sGBT to Account/Card AND Paypal to Account/Card - Aviv | Estella |  | Conversion | Reduce Friction |  | P&Q/ Inrule AAS | Business Enablement |  |  | Funnel monitoring of AHA flow + events | TBD
India PWD - BE dev | Suport Person with disability flow during Signup | Compliance | P0 | 2 |  |  | Meital
User Journey optimization - Companies | Updade country+business type in quick Can be combined with LD cleanup (e.g.: phone verification) | CVR | P0 | 5 |  | Pre-requisite for India/Remove dependecy from China/ Increase CVR | Estella | [5 empty] | Business Enablement |  | Support partner token logic: Additional 1MW Remove SP from org type in Account setup - Required discovery if we want to run it as a test. 1MW Collect country before account type - 2MW Account type UI: Use different UI component - 1MW Switch UI component + DS extension - 3MW Switch + new DS components -4-5MW |  | Yes
Segmentation - Smart industry search | Help finding the right industry based on the context of customer input | CVR | P0 | 2-4 |  | Segmentation CVR | Estella
Organization type simplification | Simplify org types list to reduce friction | CVR | P0 | 2 |  | Company CVR Reduce friction and confusion on org type selection | Estella | [7 empty] | Only D2P, only Inc countries
engineering excellence - Automation coverage |  | Modernization | P0 |  |  |  | Shany | [5 empty] | Modernization |  |  |  | Yes
engineering excellence - Monitoring |  | Modernization | P0 |  |  |  | Shany | [5 empty] | Modernization |  |  |  | Yes
Partners - Consent page | Improve the consent page UX and placement | Enterprise | P0 | 2 | Reduce friction from enterprise customers | Increase CVR - around 50% drop after consent page due to redirect to Partner | Estella |  | Conversion | Reduce Friction |  |  | Business Enablement |  |  |  | Select...
Partner integration with KYC improvements | Partner integration with IDV, POR OCR | Enterprise | P0 | 4 |  | Reduce unnecessary KYC data collection and mismatches with prepopulation from vendor and OCR capabilities (ID, CVD, POR) | Estella |  | Conversion | Reduce Friction |  |  |  | Required effort from IDV side + FDC | IDV: 2.5MW POR OCR: 1.5MW
PH for split
Remove whatsapp phone verification - APAC | Some countries canno | Compliance | P0 | 1 |  |  | Ira | [7 empty] | Remove LD and add configuration
Aurora modules - Migration | Align with DS | Modernization | P0 |  |  |  | Ira | [5 empty] | Modernization |  |  |  | Yes
Aurora - Data |  | Modernization | P0 |  |  |  | Chen
KYC Orchestration - Leftovers | Ability to fallback to a document after e-collection/vendor response | CVR | P1 | 2 |  |  | Shany |  |  |  |  | profile(linda) and e-verificarion (anton) | Business Enablement | P&Q + EV |  |  | Yes
Partner data - Fix HQ vs incorporation mapping | Avoid populating HQ country instead of Inc country which causes bad UX, by aligning business country mapping with CLM logic. | Enterprise | P1 | 1 |  |  | Estella
LS - Data enrichment | 1. Build infrastucture to support data enrichment from external provider 2. explore addtional data sources enrichment sucha s Sales feedback | Lead score | P1 | 0 | Support data enrichment provider from exteral provider to improve the accuracy rate | improve the accuracy rate of potential TICP as A & B predication | Yaniv |  | Efficiency | Reduce Friction | % of leads enriched with firmographic data | Data Science team ( Yeali's team), Shachar's team . | Modernization | The direction for CLM is multiple data-rich models running in real time (risk, scoring, and more). So whatever DE builds for an offline flow gets replaced the moment we move online. In addition, offline is a more complex integration with Segment and Salesforce, and harder to ensure the most up-to-date score is sent to sales. |  |  | Yes
LS - Rank deciosn point to a later reg stage | Lead Rank will be calculated after URL/eCollection step. | Lead score | P1 | 0 | URL type will provide a great signal if customer is a seripus company - Non-generic URLs hold 84% of company ICP-10K. | improve the accuracy rate of potential TICP as A & B predication | Yaniv |  |  |  | A and B percision rate is higher than segmentation scored baseline (Approved True-ICP ÷ leads ranked A/B); Track ICP-rate of the dropped-before-URL cohort; SLA coverage shouldn't fall; | Data Science team ( Yeali's team), Support from Data dep, Elad's team, Data Analyst Team. |  | Loosing ~13% of A/B potential leads if we don't implement two stage scoring in parralell
LS - Two Stage Lead Calculation | Lead Rank will be calculated 2 times: post-segmentation and after URL/eCollection step. | Lead score | P1 | 0 | 1. We see a drop of ~13% of company A / B leads between post segmentation but before URL submitted. 2. TICP company that provided URL are 80% from all TICP. | we can still lead rank on customers who don't reach URL but did finish segmentation | Yaniv |  |  |  | A and B percision rate for both stages; SLA coverage shouldn't fall | Data Science team ( Yeali's team), Data eng., Elad's team support , Data Analyst Team. |  | harder to ensure the most up-to-date score is sent to sales.
LS - Remove blocked accounts from Lead score model | filter out high predicted blocked accounts so model won't run on them. | Lead score | P1 | 0 | Identifying high risk account and removing them from model population will reduce Sales and OPS efforts on A & B ranks | improve the accuracy rate of potential TICP as A & B predication | Yaniv |  |  |  | % of blocked accounts which wrere tagged as Lead rank A or B | Data Science team ( Yeali's team), Support from Data dep, Ido Seter, Ido Lustig.
Add company (home team) | Support the KYC flow of adding a company from an existing account | CVR | P1 |  |  |  | Chen | [5 empty] | Growth |  |  | Identify new type of registration + events + funnel monitoring | TBD
Inrule - Oscilar support | Add "update date" to API GET /api/v1/customers/{id}/phones once a phone is updated | InRule | P1 | 1 |  |  | Gary
Bank details UX - Company | Improve UX when a company adds a personal bank account | CVR | P1 | 0 |  |  | Ira | Company with personal BA – UX improvement.docx |  |  |  | MMP
Move Payer / Reveicer question to CLM | Segment the 'payer' lead without the payer/receiver question in the marketing website | CVR | P1 | 3 | We don’t need to ask the customer to segment themselves. A better approach is to ask what motivated them to sign up for Payoneer or which products they are interested in | Reduce unnecessary confusion at segmentation step; lower drop-off rate by removing a question customers struggle to answer; smoother registration flow leading to higher completion rates | Chen |  | Efficiency | Reduce Friction | payer/receiver question step drop-off rate reduction | Marketing, BLS | Modernization | measuring the direct impact of removing this step from the marketing website is likely not feasible | Update UTM, save value
Replace the segmentation questions experiment | Experiment with replacing source of funds and number of payments questions to evaluate their effectiveness for customer segmentation" | CVR | P2 | 4 | The current segmentation questions are not effectively differentiating our customer base. This experiment will validate whether replacing these questions improves segmentation accuracy, giving us confidence to implement the change permanently | Improved lead segmentation enables more relevant product offerings, potentially increasing FFT rate | Chen |  | Efficiency | Reduce Friction | Correlation between customer segments (B2B, B2C, payers, marketplace users) and their FFT payment type
Onboarding with no BA | Allow customers to onboard without providing bank account details | CVR | P2 |  |  |  | Estella |  |  |  |  | MMP, InRule
Blocked account due to duplicate account | Required product discovery. Reduce friction for customers who are blocked due to existing account. | CVR | P2 |  |  |  | Chen |  | Conversion |  |  |  | Business Enablement |  |  | Discovery required data | No
Configuration cleanup | Remove all conditions that were relevant for gradual rollout | Modernization | P2 |  |  |  | Shany
Offer WhatsApp as sole phone verification method instead of blocking potential "bot" | Block SMS for phone verification and allow only whatsapp verification for suspected BOT | CVR | P2 |  |  | Reduce friction/ increase CVR without increasing operational costs | Estella |  | Efficiency
P&P support | Support gates access flow for certain population | CVR | P2 |  |  |  | Ira |  |  |  |  | InRule/AAS, P&P
Open PS during the onboarding | allow customers to order PS during CLM onboarding | CVR | P2 |  | Reduce PS opt-in wait time to drive higher PS adoption and improve FFT rate | Hight FFT rate among companies | Chen |  | Conversion | Reduce Friction | FFT rate and PS adoption rate among companies | PS team
LS - Build the Online Model (Lead Score Service) | Replace the offline lead score model with online model. | Lead score | P3 | 8 | The offline model run every hour and based on the data in the storage. we want the score to be calculated live and the model to be API based. | Eliminate up to 1-hour scoring delay; real-time GTM prioritization; faster response to A/B leads; easier to provide most updated lead score, data enrichment can be utilized to other online flows such as Risk and KYC. | Yaniv |  | Efficiency | Reduce Friction | time to score reduction (from up to 60 min to <1 min); GTM lead response time (time from lead creation to first sales touch) | Data Science team ( Yeali's team), Support from Data dep, Segment (Moran H.) | Modernization | New flow that we will need to monitor closely for any glitches, dependency on segment and big query integration to new service. |  |  | Select...
LS - Managing email domain from internal data | Managing business email domain for leads | Lead score | P3 | 1 | connect different customers and improve data‑enrichment efficiency (short term), save leads with existing email domain the steps in onboarding (long term) | Higher converstion rate among leads from same company / email domain | Yaniv |  | Efficiency | Reduce Friction | # of email domains groups | Data Science team ( Yeali's team), Support from Data dep, Data Analyst Team (Ofir's team) | Modernization |  |  |  | Select...
Partners - reduced KYC for Lite Plan | Support lite KYC for lite plan customers who are not required to verify their address. Take in consideration the delta collection when they upgrade plans | Enterprise | P3 | - | Reduce friction from lite plan customers | Reduce friction by removing POR collection for lite Plan/ Increase CVR | Estella |  | Conversion | Reduce Friction |  | Most of the effort P&Q | Business Enablement |  |  | Plan filter in looker + Value assesment analysis | No
Payer support - Upgrade from payer to CLM receiver | Allow existing customers to become CLM hybrid customer | CVR | P3 |  | support AHA flow of existing payers to become CLM receivers | 100% compliant | Chen |  | Efficiency | 100% Compliant | % of active customer after the migration out of active customers before, % of active customer upgrade to CLM hybrid customer |  | Business Enablement
Dynamic marketing consent | Support auto-consent based on country | CVR | P3 |  |  |  | Ira
Legal Entity collection as part of Account setup | Legal Entity collection as part of Account setup | Companies | P3 |  | LE entity collection as part of Account setup, similar to what was done in China CLM | Smoother flow/ Increase CVR | Estella |  | Conversion
LS - China Model (Not required RND resources) | Tailored scoring for CN leads with distinct CLM flow; | Lead score | P4 |  | improved China market prediction accuracy | higer accuracy of A in China | Yaniv |  | Efficiency | Reduce Friction | The precentages of real A in predication A | Data Science team ( Yeali's team), Support from Data dep, Data Analyst Team (Ofir's team) | Business Enablement |  |  |  | Select...
WL - T&Cs link don't mention Payoneer |  | 4step - Enterprise | P4 |  |  |  | John
Bug - Phone country MM | When country = Palestine AND Phone country = Not Palestine, THEN customer gets error and can't onboard | 4step - Enterprise | P4 |  |  |  | Daniel Bourbia | PBI
Note on A30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Estella Cherques Balassiano @Shany Levi worth considering including this item as we discussed with Yoav.
Note on A34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Shany Levi after our meeting today can I remove it? Reply: yes

## Fast followers
Priority | Population | Item | Status | Dependencies
1 | Enterprise - Non China | e-Collection support for partners | Pending testing
2 | ALL | Context based industry search | Not started
3 | Companies | Simplify org type list | Product discovery | CMR
4 | ALL | Signup: - Switch between county and business type questions - Add SP to the business type question (indi/SP/comp) | Not started | Mobile app Dependency for India flow
5 | D2P | Update list of Marketplaces (BS) | Not started | Pricing team
CUTLINE
6 | Enterprise partners with consent (eBay) | Move consent page to after submitting all documents | Not started | Mobile app
7 | Enterprise - Non China | IDV support for partners | Not started
8 | All - Non China | Include segmentation in account setup | Not started
9 | Enterprise - Non China | POR - Contextual collection with OCR for partners | Not started | Dependency on DU team
10 | Mobile | Prepopulate phone verification code | Not started
11 | ALL | Block old devices from registration | Not started