The Foundry — AI Academy & Community

Workstream Snapshot — March 2026

Workstream Lead: Yonatan Orpeli (VP Product, CLM)

Date: March 26, 2026

The Foundry is Payoneer's AI skills and education program, designed to raise AI capability across the entire organization through two complementary pillars: a structured Academy for deep, cohort-based training, and a broad-access Community that ensures no one is left behind.

This is a new initiative. The first cohorts and community activities will be learning experiments — we expect to iterate on format, content, and delivery as we go.

1. End-State Vision: Target Architecture (To-Be)

An organization where every employee has a baseline of AI fluency, top practitioners are certified through rigorous tracks, and a self-sustaining community keeps knowledge flowing across business units — continuously.

Key Building Blocks

| Building Block | Description |
| --- | --- |
| Learning Tracks (Academy) | Four-tier certification: Makers (personal productivity) → Builders (team-level solutions) → Masters (architecture & platform) → Wizards (top AI ambassadors). Role-specific tracks starting with Product and Engineering, expanding to more functions. |
| Content & Access (Community) | Curated content library from Academy materials plus original content. "AI for All" programming — live sessions, events, and self-serve resources accessible to all Platform employees. |
| Faculty & Governance | 80% internal faculty (contextual, product-aware) + select external advisors. Foundry Board for strategic oversight. Academic Council for curriculum consistency and certification standards. |
| Certification Gates | Rigorous progression gates between levels — learners demonstrate real-world impact before advancing. Validated by managers, peer demos, and security checklists. |
| Knowledge Network | AI champions embedded across BUs, cross-functional meetups, internal community channel, project showcases. Alumni feed back into the community as mentors and content creators. |
| Platform (LMS) | Learning management system for content delivery, progress tracking, and certification — in planning, not yet selected. |

What Exists Today vs. What Is Missing

| Exists Today | Missing / In Progress |
| --- | --- |
| Full Product track syllabus (14 sessions across Makers + Builders) | Content not yet validated with real cohorts |
| Full Engineering track syllabus (23 sessions across M1–M3 + B1) | LMS platform not yet selected or deployed |
| Session leads assigned (9/14 Product, 12/23 Engineering) | Community format and programming still being shaped |
| Three-tier certification model designed (Makers, Builders, Masters) | Wizards tier not yet designed |
| Governance model defined (Foundry Board, Academic Council) | Governance bodies not yet staffed |
| Registration and launch timeline set | Metrics and tracking infrastructure not live |

Main Workstream Outputs

- Complete Academy syllabus — both Product and Engineering tracks

- Certification gate framework (3 gates with prerequisites, deliverables, and impact thresholds)

- Two-pillar program structure (Academy + Community) with clear ownership

- Executive briefing materials and internal communications

- Session lead recruitment and assignment

2. Quick Wins — Status & Value

| # | What (Use Case) | Status | Impact | Insight |
| --- | --- | --- | --- | --- |
| 1 | Full dual-track syllabus designed — 37 sessions across Product (14) and Engineering (23), structured into Makers/Builders tiers | Done | Shared framework for all session leads; recruitment of faculty based on concrete session descriptions | Designing both tracks simultaneously forced alignment on shared ceremonies and joint sessions — worth the extra coordination |
| 2 | Session lead recruitment — 21 of 37 sessions have assigned leads from across Product and Engineering | In progress | Distributed ownership reduces single-point-of-failure; builds faculty bench | Internal volunteers bring domain context external trainers can't; optimize for their convenience, not process overhead |
| 3 | Community pillar defined — "AI for All" track and content management model scoped alongside Academy | In progress | Ensures the broader org isn't left behind while select cohorts go deep; signals inclusivity | Separating Academy (depth) from Community (breadth) avoids the trap of trying to do both in one format |

3. From Experiment → Capability

This is a new program. The first cohorts are explicitly experiments — designed to learn what works before scaling.

| Quick Win | POC / Tool / Capability? | Architecture Mapping | Required to Scale | Expected Adoption |
| --- | --- | --- | --- | --- |
| Dual-track syllabus | Scalable capability — the curriculum architecture for all future tracks | Defines learning tracks, certification gates, and progression model | Content validation from first cohorts; feedback loops built into delivery | First cohort: 60–80 learners across PM + Eng. Expanding to additional roles in subsequent rounds |
| Session lead network | POC — testing internal faculty model | Validates the 80% internal / 20% external faculty approach | Session lead enablement; content quality bar; ongoing faculty recruitment as tracks expand | 21 leads today; grows with each new track and cohort |
| Community pillar | POC — format and engagement model still being defined | Validates broad-access delivery (events, content library, champions) | BU-level AI champions identified; content pipeline from Academy to Community; engagement tracking | Target: all Platform employees have access; active engagement measured by event attendance and content consumption |

4. Dual Horizon Plan

Next 6–12 Weeks (Execution)

| # | Milestone | Owner | Deliverable | Key Dependencies |
| --- | --- | --- | --- | --- |
| 1 | Program announcement and registration | Yonatan + Omer | Public announcement, registration form, cohort selection criteria | Final syllabus confirmation; exec sponsorship |
| 2 | First Academy cohort launches (post-Passover) | Yonatan (Product) + Tal (Engineering) | First sessions delivered to 60–80 learners across both tracks | Session lead content readiness; LMS or delivery platform decision |
| 3 | Community pillar kickoff | Itai Haetzni | First "AI for All" events and content published | Community format finalized; initial content curated from Academy materials |
| 4 | LMS platform decision | Yonatan + Omer | Platform selected and initial configuration | Vendor evaluation; budget approval |
| 5 | First certification gate executed | Yonatan + Tal | Makers L2→L3 gate criteria validated with first cohort | Cohort progress through initial sessions; manager validation process defined |

6–18 Months (Foundry at Scale)

What fundamental change will occur:

AI fluency becomes an organizational baseline, not a niche skill. Every employee has access to structured AI education, and top practitioners are certified through a rigorous, internally-recognized progression.

What will look materially different:

People: A network of certified AI practitioners (Makers, Builders, Masters) embedded across every BU. Wizards — top AI ambassadors — leading cross-org knowledge transfer. Internal faculty teaching from real Payoneer context.

Process: Continuous intake — new cohorts running regularly, not as one-off events. Academy content feeds Community automatically. Certification gates ensure quality. Alumni mentor new cohorts.

Product: AI-augmented workflows becoming the default for trained teams. Measurable productivity gains from Makers certification. Team-level AI solutions emerging from Builders cohorts.

Future option — Foundry Commando Team: A dedicated strike unit for high-ROI use cases, operating in 2–6 week sprints paired with squads to accelerate adoption and inject best practices back into the Foundry. To be explored once Academy graduates produce a critical mass of AI-capable practitioners.

5. Metrics — From Learning to Impact

| Question | Answer |
| --- | --- |
| What is measured today? | Session lead assignment coverage (21/37). Syllabus completeness (both tracks designed). Registration pipeline (not yet open). |
| What should be measured next? | Cohort completion rates. Certification gate pass/fail rates. Self-reported productivity gains from Makers graduates. Content consumption and event attendance (Community). NPS from first cohort. |
| When will we be able to measure? | Cohort metrics: 6–8 weeks after launch (May–June 2026). Community engagement: immediately after first events. Productivity impact: 3–6 months post-certification (requires baseline). |
| Gaps in measurement? | No baseline for pre-training AI proficiency — need to establish before first cohort. LMS tracking depends on platform selection. Community engagement metrics need definition. Long-term ROI measurement (productivity uplift, cycle time) is an industry-wide challenge. |

6. Risks & Trade-offs

| # | Risk | Type | Mitigation |
| --- | --- | --- | --- |
| 1 | Content quality not meeting expectations — sessions designed but not yet validated with real learners | Execution | First cohort is explicitly a pilot. Built-in feedback loops after every session. Iterating content based on learner experience, not theory. |
| 2 | LMS platform delays impacting launch timeline | Technical | Can launch initial sessions without LMS (simple docs + live sessions). LMS is an enabler, not a blocker for first cohort. |
| 3 | Faculty bandwidth constraints — session leads are volunteers with day jobs | Organizational | Optimize for their convenience (simple content formats, no heavy tooling). Omer coordinating directly with leads. Position as career development opportunity. |
| 4 | Community engagement risk — "AI for All" may struggle for attention without clear value proposition | Organizational | Anchor to concrete events and visible quick wins. Use Academy content as the draw. Identify BU-level champions to drive local adoption. |

Real Trade-offs

Depth vs. breadth: The Academy goes deep with a few; the Community goes wide with everyone. We're running both simultaneously rather than sequentially — this is harder to manage but ensures the org doesn't split into AI haves and have-nots.

Internal faculty vs. external experts: 80% internal means contextual and relevant, but puts load on volunteers. We're choosing relevance over polish and supporting leads with content development assistance.

Launch speed vs. content perfection: We're launching with "good enough" content and iterating, rather than waiting for perfect materials. The first cohort knows they're pioneers, not passengers.

7. Decisions Needed

| # | Decision | Why It Matters | Who Decides |
| --- | --- | --- | --- |
| 1 | Executive sponsorship confirmation — formal organizational commitment to the Foundry and cross-BU participation | Without this, cohort recruitment depends on goodwill. With it, the program has institutional weight. | Oren Ryngler (CPO) / Mor Barazani |
| 2 | LMS platform selection — which system will host content, track progress, and manage certifications | Affects scalability, learner experience, and measurement capability. Delay here is manageable short-term but blocks scale. | Yonatan + Omer + IT |
| 3 | BU ownership model for Community — how AI champions are nominated and accountable per business unit | Without named DRIs per BU, community engagement stays grassroots and uneven. | Yonatan + Itai + BU leads |

8. Overall Self-Assessment

| Dimension | Rating | Explanation |
| --- | --- | --- |
| Proof of Value | Yellow | Program architecture is complete and well-designed. But value is proven when real cohorts graduate and apply what they've learned — we're pre-launch. |
| Scalability Potential | Green | Multi-track model designed to expand to new roles. Community pillar extends reach to entire org. Faculty model (80% internal) scales with org growth. |
| Architectural Clarity | Green | Academy: clear tracks, tiers, gates, governance. Community: pillars defined, ownership assigned. Gap: Community format details still being shaped. |
| Measurement Maturity | Yellow | Key metrics identified (completion rates, certification gates, productivity uplift). No tracking infrastructure live yet — depends on LMS selection and first cohort launch. |

Summary

| Dimension | Answer |
| --- | --- |
| Top Quick Win | Full dual-track syllabus (37 sessions) with 21 session leads assigned — the curriculum backbone is built |
| Proven Value | Program design validated through industry research and internal stakeholder alignment. Real validation comes from first cohort outcomes. |
| Scalable Capability | Academy tracks expand to new roles; Community scales to all employees. Certification model and faculty network are the scaling mechanisms. |
| Architecture Readiness | End-state designed: 4-tier certification, dual-pillar structure, governance bodies, faculty model. Gap is LMS platform and Community format details. |
| Next 6–12 Week Focus | Launch first Academy cohort (April 26), kick off Community pillar, select LMS, execute first certification gate |
| Biggest Risk | Content not yet validated with real learners. First cohort is the critical proof point. |
| Key Decision Needed | Executive sponsorship confirmation to unlock cross-BU participation and institutional commitment |
| Overall Status (R/Y/G) | Yellow |

Overall: strong program design and clear architecture, but pre-launch. Moving to green requires first cohort delivered and initial learner outcomes validated.

Track Leaders & Staff

Leadership

- Tal Arnon

- Yonatan Orpeli

Staff

- Topaz Eitan

- Shilhav Ben-David

- Hisham Abdulhalim

- Odaya Caspi

- Eli Zilbershmidt

- Yonatan Ramot

- Gal Benedek

- Lior Rosenberg

- Matan Hager

- Almog Azlan

- Daniel Ostrovsky

- Noa Buchman