AI NATIVE TRANSFORMATION

PLAYBOOK

A replicable 30-day sprint for building AI-native operating models

What this playbook delivers Step-by-step process, prompts, templates, and facilitation guides to take a leadership team from executive decision to a portfolio of AI-native transformation plans — fully resourced with embedded engineers. Sprint duration: 30 days from kickoff to prioritized, resourced plans Engineering commitment: Engineers embedded into functional teams for 6-12 months Key output: Stack-ranked, business-outcome-tied transformation plans by function

Version 1.0  |  Based on a real sprint run at a B2B SaaS company  |  Confidential

# What 'AI Native' Actually Means

Being AI native is not about adding AI tools to what you already do. It is about redesigning how work actually happens — starting from a blank page, with the assumption that AI is core infrastructure.

The question is not 'where can we use AI?' The question is: 'if we were building this function from scratch today, how would we actually run it?'

| AI-Enabled | AI Native |
| --- | --- |
| AI tools added to existing workflows | Workflows redesigned from first principles around AI capabilities |
| Individual productivity improvements | Systemic operating model transformation |
| AI as a feature or add-on | AI as core infrastructure — the default, not the exception |
| Incremental modernization | Full spectrum: modernization through reinvention |
| Teams learn to use AI tools | Engineers embedded into functions; work is rebuilt, not retrofitted |
| Output: faster at existing work | Output: fundamentally different work, at fundamentally different leverage |

If you want the TLDR on how to get started with an AI-Native transformation...

- Require every team to map the end-to-end workflow and defend the stack rank with business outcomes

- Empower everyone to go fast and experiment

- Enable the broader effort with core AI infrastructure tooling

- Fund the top bets with embedded engineering squads

- Celebrate the wins, learnings and lessons along the way

This basic approach is the engine to turn 'AI curiosity' into an AI-native operating model.

# The Formula at a Glance

The sprint follows a fixed sequence. Each phase has a defined purpose, gate criteria, and output. The phases build on each other — do not skip or reorder them.

The Formula for AI Native

Commit → Sprint → Constrain → Review → Refine → Commit (Portfolio) → Embed → Industrialize

| Phase | Timing | Key Output | Gate to Advance |
| --- | --- | --- | --- |
| 1. Executive Decision | Day 0 | Named sponsor + transformation narrative | Sponsor named; resources earmarked; message consistent |
| 2. Company Kickoff | Days 1-2 | All-hands sprint charter | Everyone hears the message; expectations are unambiguous |
| 3. Functional Planning Sprint | Days 1-30 | Draft plans + workflow maps + stack rank | Plans tied to business outcomes; priorities are defensible |
| 4. Constraints Labs | ~Days 8-14 | Bottleneck submissions + Kill/Iterate/Operationalize | Measurable improvement demonstrated + durability plan exists |
| 5. Midpoint Plan Reviews | ~Days 15-22 | Reviewed drafts + structured feedback | Leaders show end-to-end workflows; can defend dependencies |
| 6. Refinement Prompts | ~Days 22-28 | Revised plans + sharper stack rank | Top 3 bets are crisp; tradeoffs are explicit |
| 7. Final Presentations | Days 29-35 | Final plans + portfolio stack rank | Exec sponsor and CTO sign off |
| 8. Portfolio Decision | ~Day 35 | Portfolio memo + resourcing plan | Top bets chosen; others deferred with reason |
| 9. Embedded Engineering | Day 30+ | Functional leader + embedded engineers delivering production outcomes | Business metrics moving; tools not demos |

# Phase-by-Phase Operating Guide

PHASE 1 Executive Decision & Framing

Timing: Day 0 Objective: Establish that AI-native transformation is a strategic investment decision — not an IT project, not optional, and not incremental. The executive sponsor makes the decision and owns the narrative.

Actions: → Executive sponsor (President / CEO / Board member) makes a clear, named commitment to the transformation → Frame the challenge: what business goal will not close under the current operating model? Why now? → Establish the 'build from scratch in [year]' lens — this is not an optimization exercise → Name the exec sponsor, CTO/technical lead, and program lead; earmark engineering resources → Prepare the All Hands message — this is the launch event, not just a communication

Gate / Outputs: ✓ Sponsor named; resources earmarked; narrative is consistent ✓ CTO and top engineer are aligned and engaged ✓ Message is ready to deliver company-wide

PHASE 2 Company Kickoff (All Hands)

Timing: Days 1-2 Objective: Make the sprint real and visible to the entire company. Remove ambiguity about scope, timeline, and expectations. The forum can be any company-wide communication — what matters is that everyone hears it.

Actions: → Executive sponsor presents the transformation challenge and 30-day sprint process to the whole company → Share the initial leadership prompt broadly — not just with senior leaders → Set the timeline explicitly: Day 0, Day 15 (midpoint), Day 30 (plans due), Day 35+ (finals) → Communicate: this is not extra work — this is the work that makes the plan a reality → Establish that senior leaders own the timeline for their teams

Gate / Outputs: ✓ Everyone has heard the same message ✓ Scope and expectations are unambiguous ✓ 30-day sprint charter is live; calendar holds are in place

PHASE 3 Functional Planning Sprint

Timing: Days 1-30 (concurrent with Phases 4-6) Objective: Every functional area leader builds an AI-native transformation plan using the standardized prompt and template. The sprint runs concurrently with the Constraints Lab, midpoint reviews, and refinement prompts.

Actions: → Each leader applies the initial planning prompt (Prompt 1) with their team → Plans start with mission and outcome clarity before jumping to workflows or tools → Teams assess: repetitive/error-prone work, bottlenecks, data gaps, and automation opportunities → Draft plans delivered by Day 15 using the standardized plan template → Plans are shared across the leadership team — leaders read and learn from each other's plans → Final plans delivered by Day 30

Gate / Outputs: ✓ Every function has a draft plan by Day 15 ✓ Plans are tied to business outcomes — not just functional efficiency ✓ Plans use the standardized template (see Section 5)

PHASE 4 Constraints Lab

Timing: ~Days 8-14 Objective: A focused and company-wide 2-day sprint, broken into functional areas, to identify a real bottleneck and use AI/automation to measurably reduce or remove it. NOT a hackathon or demo contest — a systems intervention.

Actions: → Kick off after teams have had ~1 week to think through 'the why' behind their teams and definitions of success → Each participant or team identifies at least one real/day-to-day bottleneck — not a new feature or product idea — and a blocker that slows the whole system → Measure a clear before/after baseline — no unmeasured improvement counts → Operate within pre-approved tools, data boundaries, and guardrails → Every surviving project must have an owner, be logged with IT, and have documentation → End with a Kill / Iterate / Operationalize decision for each project

Gate / Outputs: ✓ Measurable improvement demonstrated (before/after with a quantified delta) ✓ Durability plan exists: owner, logging, documentation, monitoring, retirement plan ✓ Kill/Iterate/Operationalize decision made for each submission

Pro Tip: Host Leadership Roundtables After the Constraints Lab

Before jumping into midpoint reviews, set aside time for your functional leaders to sit together in an informal roundtable — no slides, no formal presentations.

Let leaders openly share: what they've learned so far, what surprised them, decisions they've made (and why), dragons they've slain, tools they've tried, and where they're stuck.

This accomplishes three things: it creates peer energy and healthy competition, it surfaces cross-functional patterns and dependencies that no one sees in isolation, and it builds collective ownership of the transformation — this is not just 'my team's plan,' it's ours.

The format should be loose and conversational. The exec sponsor should participate but not dominate. The best insights come when leaders feel safe sharing what didn't work, not just what did.

PHASE 5 Midpoint Plan Reviews (45-minute sessions)

Timing: ~Days 15-22 Objective: Small-group review sessions with the exec sponsor, CTO, and top engineer. Leaders present draft plans and receive structured feedback. Goal: stress-test plans and push toward real workflow redesign.

Actions: → Pre-read required: reviewers read draft plan documents before the session → Leaders present: overview, challenges, opportunities, stack-ranked priorities + reasoning, critical bottlenecks → Review panel: exec sponsor, CTO, top engineer (keep it small and senior) → Common feedback to push: end-to-end workflow maps (boxes, lines, decision points, system interactions), tighter stack rankings, modernization vs. reinvention → Follow up with written feedback within 24 hours

Gate / Outputs: ✓ Leaders can show end-to-end workflows with triggers, decision points, handoffs, and systems ✓ Stack ranks are defensible with explicit tradeoffs ✓ Each team knows what 'reinvention' looks like for their function vs. pragmatic modernization

Pro Tip: Open the Plans to Everyone — and Require Cross-Reading

Host all functional plans in a single shared folder that is visible to every functional leader. Not just their own plan — all of them.

Then explicitly ask every leader to read every other leader's plan before finals. This is not optional encouragement — make it a named expectation.

Why this matters: leaders designing in isolation build locally optimal plans. Leaders who read each other's plans spot dependencies ('your workflow feeds into mine'), find shared needs ('we both need the same Salesforce connector'), avoid duplication, and raise their own bar when they see peers pushing further.

The best plans get better when leaders are inspired — and constructively challenged — by what their peers are doing. Make the folder the connective tissue of the sprint.

PHASE 6 Refinement Prompts

Timing: ~Days 22-28 Objective: After midpoint feedback, the exec sponsor and technical lead share targeted prompts to push teams to sharpen plans, tighten stack rankings, and be intentional about modernization vs. reinvention.

Actions: → Exec sponsor shares Refinement Prompt (Prompt 3) to all senior leaders → Top technical leader shares technical enablement prompt (Prompt 4) in parallel → Leaders must address: business outcome linkage, stack rank reasoning, cross-functional dependencies, execution clarity → Push leaders to align with business system owners (CRO, CFO) on sequencing and leverage → Require explicit 'what we are NOT doing' list with reasoning

Gate / Outputs: ✓ Top 3 bets per function are crisp with impact math ✓ Explicit 'not doing' list with reasoning exists for each plan ✓ Cross-functional dependencies are mapped and named

PHASE 7 Final Presentations

Timing: Days 29-35 Objective: Leaders present finalized plans to the full review panel. This session is the gateway to the portfolio decision and engineering resource allocation.

Actions: → Final plans delivered using the standardized template → Leaders present: executive summary, business outcomes, workflow maps, stack-ranked bets, dependencies, execution plan, resource model → Review panel: exec sponsor, CTO, top engineer, and business system owners (CRO, CFO) → Each leader explicitly presents risks, dependencies, and what they are not doing → Plans must be ready to be compared and stack-ranked across functions

Gate / Outputs: ✓ Executive sponsor and CTO sign off on each plan ✓ Every plan has a defensible #1, #2, #3 with business outcome linkage ✓ Plans are ready for portfolio comparison and resourcing decisions

PHASE 8 Portfolio Stack-Rank & Engineering Allocation

Timing: ~Day 35 Objective: The executive team reviews all functional plans and makes a portfolio decision: which bets get funded with embedded engineering, which are deferred, and which are killed.

Actions: → Apply the portfolio scoring rubric to all submitted bets → Prioritize bets that move primary business levers, remove cross-functional bottlenecks, and build shared components → Allocate engineers — pulled from core engineering teams and embedded full-time into functional teams → Publish the portfolio memo: funded bets, deferred bets, shared enablement investments, key risks, review cadence

Gate / Outputs: ✓ Portfolio memo signed by exec sponsor: funded / deferred / killed with reasoning ✓ Engineering squads assigned and fully embedded into functional teams ✓ Quarterly portfolio review cadence established

PHASE 9 Embedded Engineering

Timing: 6-12 months, potentially permanent Objective: High-capacity engineers embed directly with functional leaders — no intermediate PM layer. The functional leader IS the product owner: defining requirements, mapping workflows, owning metrics, and analyzing data. Engineers connect to the CTO/top engineer for technical direction.

Actions: → Each funded bet gets a lean unit: functional leader (as product owner) + 1-3 high-capacity engineers with strong business context → Functional leader owns the what and why: requirements, workflow design, success metrics, data analysis, priorities → Engineers own the how and build: connected to CTO/top engineer for technical direction, architecture, and platform alignment — not managed into the functional org → No intermediate PM or product owner role — that layer is redundant when functional leaders are expected to do the work → Engineers spend real time in the business context: sitting in team meetings, understanding the workflows they're replacing, not just receiving tickets → Every persistent workflow must have an owner, be logged with IT, and have documentation and monitoring → Kill criteria: every bet declares what must be true by Day 60/90 — if not met, stop or revert

Gate / Outputs: ✓ Production outcomes with adoption metrics — not demos ✓ Business metrics moving vs. baseline within 90 days for Bet #1 ✓ Shared enablement layer reducing rebuild cost for subsequent bets

# The Prompts: Exact Language to Use

These are the actual prompts used in the sprint. Use them verbatim or adapt the framing to your company's voice — but preserve the core questions and demands.

## Prompt 1: Initial Planning Prompt

When to use: Delivered at the All Hands kickoff and shared in writing with the full leadership team.

Set the tone — opening framing

This isn't extra work. This is the work that makes our plan and commitments a reality.

Starting [Day 0], we begin a 30-day sprint to define what AI-native looks like inside every team.

The lens to apply: approach this as if we were building your function from scratch in [year]. This is explicitly NOT an 'optimize what we do today' exercise. It's: 'if this team didn't exist yet — and AI was native — how would we run it?'

I don't expect perfection. The landscape is moving too fast for that. I expect clarity, urgency, and action.

### Step 1: Clarity of Mission → Clarity of Metrics → Clarity of Automation

Before jumping to workflows or tools, every leader must answer:

- What outcome(s) do we exist to drive?

- How do those outcomes tie directly to revenue, margin, speed, CX, and/or platform leverage?

- What 3-5 metrics truly define success?

- Are our OKRs measuring outputs... or outcomes?

- If we removed 50% of our activity, which metrics would still matter?

Then assess your function across four dimensions:

- Repetitive, Time-Intensive, Error-Prone Work (if it feels like a grind, it's a candidate)

  - What are humans doing repeatedly that software or agents should handle?

  - What depends on tribal knowledge?

  - Where do we accept manual reconciliation as 'just part of the job'?

- Bottlenecks (if it slows growth or customer value — it matters)

  - Where does work stack up?

  - Where are decisions always waiting on 1-2 people?

  - What elongates TTV, TTFP, or revenue realization?

- Data Gaps

  - Where are we making decisions on instinct vs. data?

  - What data do we have but aren't leveraging?

  - What dashboards should exist but don't?

- Automation Opportunities

  - Where could copilots reduce cycle time?

  - Where could agents own workflows end-to-end?

  - Where are people required for validation or decisions in workflows?

### Step 2: Deliver Your Plan

| 1. Mission & Metrics | Clear articulation of team purpose; 3-5 outcome-based metrics; any changes to current OKRs |
| --- | --- |
| 2. Current State | Top time drains; top bottlenecks; top data gaps |
| 3. AI-Native Design | How the function would operate if built today; where automation and agents are embedded by default; where verification happens; where decisions happen and who/what makes them |
| 4. 90-Day Action Plan | Stack-ranked priorities; what to implement immediately; what requires cross-functional partnership; what requires platform investment — NOT a tooling wishlist |
| 5. Expected Impact | Hours saved; cycle time reduced; error rate reduced; revenue accelerated; margin improved; CX improved — if it doesn't change CX, speed, quality, cost, or revenue, it's not meaningful |

Hold this standard:

30 days from now, this cannot look like incremental improvement.

If a plan reads like 'we'll use AI to summarize notes' or 'we'll explore automation tools,' you didn't push hard enough.

Be bold. Challenge your team structure, workflows, metrics, and assumptions.

Some of what you propose may be wrong. That's fine. The cost of inaction far exceeds the cost of a few wrong bets.

## Prompt 2: 10-Day Check-In

When to use: Sent ~10 days into the sprint to maintain energy and sharpen focus before midpoint reviews.

- Ensure you are crystal clear on your 'why' and the outcomes your team exists to deliver — spend disproportionate time here

- Do not allow planning sessions to devolve into complaint sessions — bring people back to 'why' and require solutions

- Explore the latest tools in parallel; no engineering degree required to start building and adding value

- Start clarifying bottlenecks and critical enablers — name them and define what an ideal state looks like

- Where teams are ready and have high-priority items, lean in and start learning faster — it's not a race, but don't wait when you have readiness

Note on pacing

Some teams will be further along than others — and that's expected.

Where you have teams that are ready and with high-priority items, lean in to start learning faster.

As teams are building plans, technical leadership is working to get core infrastructure and enabling pieces in place. More to come on that.

## Prompt 3: Post-Midpoint Refinement (From Exec Sponsor)

When to use: Sent to all senior leaders after midpoint review sessions. Surfaces the key themes from the reviews and sets requirements for final plans.

Opening framing

Thank you. The quality of thinking, energy, and engagement across your AI Native plans has been excellent.

A number of these point toward real shifts in how the company operates — not just incremental improvements. That's exactly what we needed.

A few themes to address as you refine toward finals:

### Theme 1: Push system-level thinking further

- Reward the move toward system vs. function thinking and automation of end-to-end workflows (not just tasks)

- Teams still operating at a functional level need to zoom out to the full system

### Theme 2: Be intentional — pragmatism vs. reinvention

- Where are we intentionally staying grounded vs. where are we reimagining? Make this explicit.

- If we were building this function fresh today, would we design it this way? Pressure-test that.

- In several plans there is still room to push further on first-principles design

### Theme 3: Sharpen the connection to business outcomes (the single biggest opportunity)

Every plan must tie directly to one or more of these levers:

- Revenue / ARR

- aTPV / monetization

- Margin / cost structure

- Speed: TTV, TTFP, cycle time

- NRR / expansion

For each initiative, answer: if this works, what moves — and by how much?

### Theme 4: Stack ranking and focus

- Too many parallel initiatives without clear tradeoffs — tighten this

- Be explicit about what is #1, #2, #3 — and what you are NOT doing and why the order matters

- Align with business system owners (CRO, CFO) on top priorities and sequencing

### Theme 5: Cross-functional system alignment

- Where does your work plug into upstream/downstream teams?

- What dependencies need to be explicit?

- Where are we assuming handoffs that aren't actually defined?

### Theme 6: Execution clarity

- Clear owners — one name, not 'the team'

- Explicit sequencing with reasoning

- Measurable checkpoints: Day 30 / Day 60 / Day 90

Required next steps

Read and be inspired by each other's plans

Continue iterating with the written feedback you've received

Align with business system owners on priorities and sequencing

Tighten business impact, stack ranking, and cross-functional dependencies

Address team implications: composition, skills, gaps

Hint: use these prompts, feedback, and docs as inputs to score your own plan before final submission

## Prompt 4: Technical Enablement Prompt (From Top Engineer / CTO)

When to use: Sent in parallel with Prompt 3, from the senior technical leader. Communicates what the central engineering team is building as shared infrastructure.

Purpose of this prompt: Prevent functional teams from trying to build their own technical plumbing. Show them what will be provided centrally so their plans can focus on the business problems, not the infrastructure.

### What We're Building for You

- A Development Platform: a standardized environment where teams can build, deploy, and run AI-powered internal tools — with a database, AI/RAG capabilities, and a non-engineer-accessible interface so teams can focus on solving business problems, not technical plumbing

- Common Shared Connectors: centrally built integrations to the systems that appeared in nearly every AI-native plan — e.g., CRM, data warehouse, ERP. Built once, consumed by all squads.

- A Suite of Agents: connecting dots between functional team tools for end-to-end delivery; evolves as plans mature

| Weeks 1-2 | Infrastructure buildout + AI harness for non-technical users |
| --- | --- |
| Weeks 3-4 | First functional team pairing + first internal app live (dogfood our own tech) |
| Weeks 5-6 | Platform open for additional teams; documentation published; access via standard request process |

In your plans, explicitly identify: which connectors and shared components you need vs. what you'll build yourselves. This dependency list is how the engineering team sequences platform work.

# The Constraints Lab: Full Guide

A focused 2-day sprint — typically around Days 8-14 of the functional planning sprint — for the whole company to identify a real bottleneck and use AI/automation to measurably reduce or remove it.

What makes this different from a hackathon

NOT a feature hackathon. NOT a demo contest.

It is a systems intervention: a time for everyone to sharpen the axe, remove blockers, and create opportunities to build and operate faster.

Success = a measurable before/after delta + a durability decision (Kill / Iterate / Operationalize).

A 'win' that makes one team faster but slows the overall system is NOT a win.

## Goal & Success Criteria

A team succeeds if they can:

- Define the bottleneck clearly: what it is, where it happens, why it matters

- Demonstrate measurable improvement (before/after with a quantified delta)

- Make a clear recommendation: Kill / Iterate / Operationalize

A successful project:

- Removes friction from a pervasive issue without adding long-term risk or operational debt

- Has an explicit owner and is documentable

- Could be adopted by other teams with minimal rework

## Guardrails

### 1. Pre-Approved Tool List

During the sprint, teams may only use tools from a pre-approved list. If a critical tool is missing, request approval before the Lab begins. Establish a fast-track approval path (procurement + IT + InfoSec + Legal expedited review).

### 2. Data Boundaries

- No customer PII or sensitive customer data used as inputs in any unapproved external tool

- All data use must comply with your company's data classification policy

- If unsure: escalate to IT/InfoSec before using — not after

### 3. Logging and Traceability

If an experiment becomes a persistent workflow, it must have:

- IT registration and logging

- A named owner

- Basic documentation: what it does, where it runs, how to maintain it

## Durability & Ownership Rules

The invisible entropy problem

A common failure pattern: a team builds a great automation, it works for a while, then priorities shift or ownership changes. If it breaks later, others end up reverse-engineering and supporting something they didn't design.

The durability rules below prevent this. Enforce them from the start.

Every surviving project must define:

| Field | What to define |
| --- | --- |
| Owner | One named person who owns the workflow long-term — not 'the team' |
| IT Support | What level of support does IT need to provide? How is it logged? |
| Documentation | What it does, where it runs, how to maintain it, and what to do if it breaks |
| Monitoring | How will you know if it degrades or breaks? What are the alerts? |
| Retirement Plan | Under what conditions would you shut this down? Who decides? |
| Cross-Team Impact | Does this change interfaces with other teams? Document new handoffs or dependencies. |

## Kill / Iterate / Operationalize

Kill

The bottleneck wasn't as significant as expected, OR the solution doesn't hold up to durability requirements. Stop now — don't let it linger.

Iterate

The approach shows promise but needs refinement. Define the next 2-week sprint: specific hypothesis, specific measurement, specific owner.

Operationalize

Measurable improvement demonstrated. Durability plan complete. Owner committed. Move to production. Register with IT. Schedule monitoring.

# Standardized Plan Template

Every functional team uses this template. Consistent structure makes plans comparable and stack-rankable across functions. The sections below are informed by real plans produced across Product/Engineering, Sales, AM/CS, Finance, Legal, People, Marketing, Analytics, IT, and Support.

## Section 1: Cover & Executive Summary

| Owner | Functional leader name and title |
| --- | --- |
| Exec Sponsor | Named executive sponsor |
| Date & Version | Submission date; status (Draft / For Review / Final) |
| 5-Line Summary | What the function does, the biggest opportunity, the top 1-2 bets, and what moves if this works |

## Section 2: Business Objective & Why Now

Describe the constraint: what business goal will not close under the current operating model? Tie directly to the business system. Avoid generic 'AI is important' framing.

- Which primary lever does this function drive: ARR / aTPV / Margin / NRR / Speed?

- What is the gap between current state and what the business requires?

- Why redesign now rather than optimize incrementally?

## Section 3: Definition of Success (The Scoreboard)

List 3-7 metrics with baselines (if known), targets, and measurement method. Include leading and lagging indicators.

| Metric | Baseline | Target | Measurement Method |
| --- | --- | --- | --- |
| [Metric 1] |  |  |  |
| [Metric 2] |  |  |  |
| [Metric 3] |  |  |  |
| [Add more...] |  |  |  |

## Section 4: Current State — End-to-End Workflow

One workflow map per core process. This is arguably the most important section. Do not submit bullet lists.

What 'end-to-end workflow' means:

Trigger: what starts the process?

Steps: each handoff, decision point, and system interaction — in sequence

Decision points: where does a human make a judgment call? What data do they use?

Systems touched: which tools, databases, or platforms are involved?

Failure modes: where does the process break down, slow down, or create errors?

Cycle-time drivers: where is the most time spent? Where does work queue?

Output: what does 'done' look like?

Examples of high-level workflow starting points by function:

- Revenue: lead → opportunity → close → onboard → expand → renew

- Finance: request → approval → execution → reconciliation → reporting

- People: requisition → source → screen → offer → onboard → develop → offboard

- Engineering/Product: signal → prioritize → build → test → deploy → monitor

- Legal/Compliance: request → intake → review → advise → execute → archive

- Support: ticket → triage → diagnose → resolve → close → feedback loop

## Section 5: AI-Native Future State

Re-map the same workflows with explicit boundaries: human vs. AI vs. automated system.

| Human Does | AI Does | System Automates |
| --- | --- | --- |
| High-judgment decisions, relationships, exception handling, creative and strategic work | Pattern recognition, synthesis, drafting, analysis, scoring, recommendation, triage, Q&A | Data movement, logging, notifications, scheduling, reporting, routine approvals, status updates |

## Section 6: Stack-Ranked Bets (#1 → #N)

For each bet, include:

| Field | What to include |
| --- | --- |
| Bet Name | Short, memorable name |
| Business Lever | Which primary metric moves: ARR / aTPV / Margin / NRR / Speed |
| Impact Math | Simple math + assumptions: e.g., delta ARR = (# deals influenced) x (delta win rate) x (avg ACV) |
| Why #N | Why this rank? Value, feasibility, dependency unlock, or risk reasoning |
| NOT Doing | Explicit list of adjacent ideas deprioritized — and why |
| Modernize vs. Reinvent | Are we optimizing the current workflow or redesigning from scratch? Be intentional about which. |

## Section 7: Dependencies & Bottlenecks

- List non-negotiable dependencies: data quality, platform connectors, product changes, system cleanups

- Name the single biggest bottleneck that would prevent Bet #1 from succeeding

- Identify cross-functional dependencies: which other teams' work does yours require?

- Flag any dependencies on the central enablement layer (shared connectors, platform)

## Section 8: Execution Plan (90 / 180 / 365 Days)

| Day 30 | Workflow maps complete; Bet #1 scoped; squad identified; baseline metrics captured |
| --- | --- |
| Day 60 | Bet #1 produces first measurable improvement vs. baseline OR kill criteria applied |
| Day 90 | Bet #1 in production with adoption plan; portfolio refreshed; Bet #2 scoped |
| 6 Months | Bet #2 in production; shared components reused; team model adjusted based on learnings |
| 12 Months | Bet #3 in production; enablement layer mature; cross-functional integration evident |

For each milestone include: owner, definition of done, risk, and kill criteria if applicable.

## Section 9: Resource Model & Team Implications

- What skills are needed: process design, data engineering, AI/ML, software engineering, change management?

- What changes in roles? What roles become less necessary? What new roles emerge?

- What will the team stop doing to create capacity for this work?

- How many embedded engineers are needed, for how long, and with what skill mix?

## Section 10: Risk, Security & Durability

Apply the same durability rules as the Constraints Lab to every persistent workflow:

- Owner: one named person, not 'the team'

- Logging: IT-registered, with monitoring and alerting

- Documentation: what it does, where it runs, how to maintain it

- Retirement plan: under what conditions do you shut it down?

AI risk tiers:

- Tier 0 (Low): internal productivity, no customer data → lightweight review + logging

- Tier 1 (Medium): internal workflow automation touching core systems → security review + monitoring

- Tier 2 (High): customer-impacting decisions or sensitive data → formal review, testing, auditability, escalation path

# Portfolio Scoring Rubric

Use this rubric in the portfolio stack-rank session to score all bets consistently and force explicit tradeoffs. Score each dimension 1-5; apply weights to get a composite score.

| Dimension | What '5' looks like | Weight |
| --- | --- | --- |
| Business Impact | Clear, measurable lift to ARR / aTPV / Margin / NRR / Speed with credible assumptions and simple impact math | 30% |
| End-to-End Leverage | Removes system bottlenecks; transforms full workflow — not local efficiency only; improves cross-functional flow | 20% |
| Time-to-Impact | First measurable movement achievable within 90 days; clear Day 30/60/90 milestones | 15% |
| Dependency Unlock | Unblocks multiple downstream bets; builds shared connectors or reusable components others can consume | 15% |
| Risk / Durability | Controls, monitoring, ownership, and retirement plan are explicit; tiered appropriately to risk level | 10% |
| Adoptability | Behavior changes identified; incentives, role clarity, and operating cadence match reality | 10% |

Impact math formulas (use as placeholders)

ARR: delta ARR = (# deals influenced) x (delta win rate) x (avg ACV)

aTPV revenue: delta Revenue = delta aTPV x take rate (bps)

Margin: delta Margin = delta Revenue - delta COGS - delta servicing cost

NRR: NRR = (Start ARR + Expansion - Churn) / Start ARR

Speed value: Annualized revenue x (delta days / 365)

## Portfolio Memo Format

The exec sponsor signs a memo with:

- Top 3 bets funded — with squad composition, engineers, and timeline

- Bets deferred — with explicit reason and re-evaluation trigger

- Shared enablement investments — connectors, platform, governance consumed by all squads

- Key risks and named mitigation owners

- Date to re-evaluate portfolio (recommend: quarterly)

# The Embedded Engineering Model

Engineers are pulled from core engineering teams and embedded directly with functional leaders for 6-12 months — potentially permanently. There is no intermediate PM or product owner layer. The functional leader IS the product owner.

Why remove the PM layer?

The traditional product owner role exists to compensate for a skill gap: functional leaders who can't define requirements, map workflows, or analyze data. That gap is exactly what this transformation closes.

If functional leaders are expected to do that work — and they should be — a PM layer just adds handoffs, slows decisions, and insulates engineers from the business context they need.

Removing it is itself an AI-native choice: fewer layers, faster loops, higher signal.

## The Model: Two Accountabilities, No Layer Between Them

| Functional Leader | Embedded Engineers |
| --- | --- |
| Owns the what and why: • Requirements and workflow design • Success metrics and baselines • Data analysis and outcome review • Priority calls and tradeoffs • Sprint direction and 'done' definition | Owns the how and build: • Technical architecture and decisions • Workflow automation and agent builds • Platform and connector integration • Technical direction from CTO / top engineer • Code quality and durability standards |

The dual accountability that makes this work

Functional leaders direct what gets built and define success. Engineers connect to the CTO/top engineer for technical direction, architecture decisions, and platform alignment.

Engineers are NOT managed into the functional org. Technical accountability stays with technical leadership.

This prevents both capture (engineers pulled into non-priority work by the functional org) and drift (engineers making architecture decisions without technical oversight).

## What This Requires of Functional Leaders

This model only works if functional leaders are genuinely doing the product work. The expectation must be explicit:

| Workflow mapping | Can document the current end-to-end workflow with triggers, decision points, systems, and failure modes — not just describe it in words |
| --- | --- |
| Requirements | Can write clear problem statements and define edge cases with enough specificity that an engineer can build without guessing |
| Metrics ownership | Owns the baseline, defines what 'working' looks like numerically, and reviews outcomes weekly |
| Data analysis | Can pull and interpret data to evaluate whether a bet is moving the needle — doesn't need an analyst to tell them |
| Sprint engagement | Attends demos, gives feedback on working software, prioritizes the backlog with real reasoning — not a passive approver |
| Capacity | Genuinely protected time for this work — not squeezed around their existing role. If they're not spending real hours in it, the model fails. |

The signal to watch for

If a functional leader starts delegating the 'product' work to engineers ('you figure out what to build'), the model has broken.

The fix is not to add a PM. The fix is to reset expectations with the leader or reconsider whether the bet is the right one to fund.

## Team Composition (Lean by Design)

| Functional Leader | The product owner. Owns requirements, workflow design, success metrics, data analysis, and priority calls. Full accountability for outcomes. |
| --- | --- |
| 1-3 Embedded Engineers | High-capacity engineers with strong business context. Embedded 6-12 months. Connected to CTO/top engineer for technical direction. Not managed into the functional org. |
| Data / Analytics Support | Shared resource or lightweight embed — helps instrument the workflow and validate metrics. The functional leader does the analysis; this role ensures the data pipeline exists. |
| Security / Privacy (as needed) | Engaged for Tier 1 and Tier 2 workflows. Lightweight review for Tier 0. |

## Operating Cadence

| Weekly | Functional leader reviews outcomes vs. baseline with engineers. Is Bet #1 moving? What's blocking? What's next? |
| --- | --- |
| Biweekly | Demo of working workflow — not slides. Functional leader sees the actual thing and gives direction. |
| Monthly | Exec sponsor checkpoint: tradeoffs, unblocks, portfolio adjustments. CTO/top engineer reviews technical direction across all embedded squads. |
| Quarterly | Portfolio refresh: are the original bets still the right bets? Are engineers in the right places? |

## Enablement Layer (Parallel Platform Track)

Run a parallel platform track — owned by central engineering — to prevent every embedded engineer from rebuilding the same plumbing:

- Standardized development platform: where engineers build, deploy, and run AI-powered internal tools

- Common shared connectors: centrally built integrations to systems that appear in multiple plans — built once, consumed by all squads

- Reusable agent harness and deployment patterns: so each engineer isn't solving infrastructure problems instead of business problems

- Clear access process: standard request path so new engineers can onboard to the platform quickly

Platform OKRs to track:

Time to onboard a new embedded engineer (from assignment to first working prototype)

% of common-system integrations delivered as reusable connectors

Stability of internal tools: documentation rate, monitoring coverage, incident rate

# of squads consuming shared components vs. building bespoke

# Common Failure Modes & How to Prevent Them

| Failure Mode | How It Shows Up | Mitigation |
| --- | --- | --- |
| Tech for tech / tool sprawl | Plans read like vendor wishlists; no business outcome linkage | Require impact math and workflow maps; fund only what moves business levers |
| Uncoordinated pilots | Different teams building similar things; no shared components | Shared templates + portfolio stack-rank + enablement layer with reusable connectors |
| Local optimization slows the company | A team automates its queue but creates a bottleneck upstream | Constraints Lab flags cross-team impacts; dependencies required in all plans |
| Invisible entropy / orphan automations | Workflows built, shipped, then abandoned when owners change | Durability rules: named owner, IT registration, documentation, monitoring, retirement plan |
| Plans without workflows | Bullet lists of ideas with no end-to-end process design | Midpoint review rejects plans without workflow maps; feedback focuses here first |
| Change management failure | Tools shipped; behavior unchanged; teams revert to old methods | Adoption milestones in plan template; weekly outcome reviews; treat as operating model change |
| Platform fragmentation | Each squad builds bespoke connectors; rebuild costs accumulate | Enablement track owns shared components; squads consume, don't rebuild |
| Agent sprawl | Too many AI workflows running without monitoring or accountability | Tiered governance; workflow inventory; autonomy boundaries documented |

# 90 / 180 / 365-Day Execution Roadmap

| Horizon | Focus | Key Gate |
| --- | --- | --- |
| Days 0-30 | All-hands kickoff; team planning with workflow maps; Constraints Lab; midpoint reviews and revisions | Every function has a draft plan with an end-to-end workflow and initial stack rank |
| Days 31-90 | Final presentations; portfolio stack-rank; squads embedded; Bet #1 MVP built; baseline captured | Bet #1 produces measurable improvement vs. baseline OR kill criteria applied by Day 60/90 |
| Days 91-180 | Bet #1 in production with adoption plan; Bet #2 scoped and squad active; shared connectors live | Business metrics moving vs. baseline; shared enablement layer serving 2+ squads |
| Days 181-365 | Bet #3 in production; platform reuse evident; cross-functional integration; portfolio refreshed quarterly | Components reused across teams; rebuild cost dropping; operating model change is durable |

# Quick Reference: Facilitation Questions

Use these questions in midpoint reviews, final presentations, and portfolio sessions to stress-test plans and push toward real transformation.

## Workflow Depth

- Show me the end-to-end workflow — boxes, lines, decision points, and systems. Not a list.

- Where exactly does human judgment happen today? What data does the person use to decide?

- What is the trigger that starts this process? What does 'done' look like?

- Where does work queue up? How long does it sit there?

## Reinvention vs. Modernization

- Are we optimizing the current workflow, or redesigning from scratch? Be intentional about which.

- If you were building this function fresh today, would you design it this way?

- What would you do if headcount were fixed and you had to double output in 18 months?

## Business Outcome Linkage

- If this works, what moves? By how much? Show the math — even if it's a range.

- How does this connect to company goals — not just functional efficiency?

- What does success look like in 90 days? How will you measure it?

## Stack Rank Sharpness

- What is #1, #2, #3 — and what are you explicitly NOT doing?

- Why does the order matter? What's the dependency or leverage rationale?

- If you could only fund one bet, which one — and why?

## Execution Confidence

- Who owns this? One name.

- What has to be true by Day 60 for this to continue? What triggers a kill?

- What are the top 2 dependencies that aren't in your control?

## Durability

- If the person who built this left tomorrow, what happens?

- Is this logged with IT? Does it have documentation and monitoring?

- What's the retirement plan — under what conditions do you shut this down?

This playbook is a living document. Update the prompts, templates, and rubric as you learn what works at your company. The structure should stay; the specific questions and examples should evolve.

# Appendix: How to Map a Real Workflow

The playbook repeatedly asks for 'end-to-end workflow maps with triggers, decision points, systems, and failure modes.' This appendix shows what that actually looks like at the level of detail required to make real engineering and design decisions.

Why this level of detail matters

The high-level workflow (e.g., 'onboard → integrate → go-live') is a starting point, not a plan.

You can't identify what to automate, where agents replace humans, or where AI changes the workflow until you've mapped every handoff, decision, system interaction, and failure mode.

If you can't draw the workflow at this level, you don't understand it well enough to redesign it. That's the point of the exercise.

## Example: SaaS Client Data Integration (Onboarding)

This example maps a single sub-workflow from a B2B SaaS implementation: the data integration step where a new client's data systems are connected to the platform. This is one piece of a larger onboarding flow — chosen because it's representative of the complexity hidden inside what most plans describe as 'onboard the client.'

High-level view (what most plans submit):

Contract signed → kickoff call → data integration → UAT → go-live

What the plan actually needs (the detail below):

### Current State: Data Integration Workflow (Detailed)

This maps one segment — 'data integration' — from trigger to completion, showing every handoff, system, decision point, and failure mode.

| Step | Trigger | Actor | Systems | Decision Point | Failure Mode | Cycle Time |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Integration kickoff | Contract signed; CRM deal status = 'Closed Won' | Implementation Manager (IM) | CRM, Project Mgmt tool, Email | IM reviews SOW to determine integration type: standard API, flat-file, or custom | SOW doesn't specify data requirements clearly; IM must chase Sales for details | 1-3 days |
| 2. Client data assessment | Kickoff complete; client data contact identified | IM + Client data team | Email, shared docs, screen share | Does client have an API? What format is their data in? What authentication method do they use? | Client doesn't know their own data architecture; delays 1-2 weeks. Client contact changes mid-process. | 3-10 days |
| 3. Integration spec created | Data assessment complete | IM (manual document) | Google Docs / Confluence, internal spec template | IM decides: can this use a standard connector or does it need custom eng work? | Spec is incomplete or ambiguous; engineer has to come back with questions, restarting the cycle | 2-5 days |
| 4. Engineering queue | Spec submitted to eng backlog | IM → Engineering lead | Ticketing system (Jira), Slack | Eng lead prioritizes against other integration requests and ongoing product work | Ticket sits in queue 1-4 weeks depending on eng capacity. Priority conflicts with product roadmap. | 5-20 days |
| 5. Integration build | Eng picks up ticket | Integration engineer | IDE, API gateway, ETL/data pipeline tools, staging env | Engineer discovers data format issues; decides whether to transform client-side or platform-side | Client API docs are wrong/outdated. Data has edge cases not in spec. Engineer blocks on client response. | 5-15 days |
| 6. Internal QA | Build complete; PR merged | QA engineer or integration engineer | Staging environment, test data sets, monitoring dashboards | Does the data pass validation rules? Do edge cases break downstream processes? | Test data doesn't represent production volume/variety. Bugs found require re-work + re-queue. | 2-5 days |
| 7. Client UAT coordination | Internal QA passed | IM + Client | Email, screen share, staging env with client access | Client confirms data looks correct in their view of the platform. Sign-off required. | Client is unresponsive for days/weeks. Client finds issues that weren't in spec. UAT scope creep. | 5-15 days |
| 8. Production deploy | Client UAT sign-off received | Integration engineer + DevOps | CI/CD pipeline, production env, monitoring/alerting | Deploy during maintenance window or rolling deploy? Rollback plan if data errors in prod? | Production data behaves differently than staging. Monitoring alerts fire. Client escalates. | 1-2 days |
| 9. Post-deploy monitoring | Deploy complete | Integration engineer + IM | Monitoring dashboards, alerting tools, support ticketing | Is data flowing correctly? Are volumes within expected range? Any error spikes? | Silent failures: data appears to flow but values are wrong. Not caught until client reports issues days later. | 5-10 days |
| 10. Handoff to support | 10-day monitoring window clean | IM → Support / CSM | CRM, support ticketing, internal wiki | Is documentation sufficient for support to handle issues without escalating to eng? | Tribal knowledge stays with IM/engineer. No runbook. Support escalates every issue back to eng. | 1-2 days |

What this level of detail reveals

Total cycle time: 30-87 days for a single integration — and the biggest driver is queue time (Step 4) and client responsiveness (Steps 2, 7), not build complexity.

The engineering bottleneck (Step 4) is a prioritization problem, not a capacity problem — integrations compete with product work for the same engineers.

The spec quality problem (Step 3) causes rework loops between Steps 3 → 5 → 3 that add weeks.

The handoff failure (Step 10) creates long-term support cost and engineer interrupt load.

None of this is visible from 'onboard → integrate → go-live.'

### AI-Native Future State: Same Workflow, Redesigned

This shows the same data integration workflow redesigned with explicit human / AI / system boundaries. The goal is not to 'add AI' — it's to redesign the workflow so that humans handle judgment and exceptions, AI handles synthesis and pattern recognition, and systems handle data movement and orchestration.

| Step | Current State | AI-Native Future State | Human/AI/System | Exception Path |
| --- | --- | --- | --- | --- |
| 1. Integration kickoff | IM manually reviews SOW and chases Sales for data requirements | Agent auto-extracts data requirements from SOW + CRM fields at deal close; pre-populates integration spec; flags gaps to IM | AI: extraction + draft. System: trigger on CRM status. Human: review + gap resolution | If SOW is ambiguous, agent flags specific missing fields to IM and Sales with suggested questions |
| 2. Client data assessment | IM manually discovers client data architecture via calls and emails over 3-10 days | Self-service client intake form (structured); agent pre-fills from known client tech stack (CRM data, public API docs); auto-classifies integration type | System: intake form + auto-fill. AI: classification + API doc parsing. Human: client completes form; IM validates | If client can't complete the form, IM escalates to a discovery call — but now has a structured starting point, not a blank page |
| 3. Integration spec | IM manually writes spec document (2-5 days); often incomplete | Agent generates full integration spec from intake data + SOW + connector library; maps to standard connector if match exists; generates custom spec only if needed | AI: spec generation + connector matching. Human: IM reviews, validates, and approves | If no standard connector matches, agent generates custom spec + flags to eng lead with estimated complexity |
| 4. Engineering queue | Ticket waits 5-20 days in eng backlog; competes with product work | Standard connectors deploy automatically (no eng queue). Custom integrations routed to embedded integration engineers with pre-built spec and estimated LOE. | System: auto-deploy for standard. Human: embedded eng for custom. AI: LOE estimation + priority suggestion | If capacity is constrained, system surfaces tradeoff to IM and eng lead with projected impact on go-live date |
| 5. Integration build | Engineer builds from scratch each time; blocks on client responses; 5-15 days | For standard: zero build time. For custom: engineer starts from auto-generated scaffold + spec; agent handles client API doc parsing and generates test cases | AI: scaffold generation + test case authoring. System: CI/CD pipeline. Human: engineer writes custom logic + reviews | If client API is non-standard or undocumented, engineer flags — but starts from a much higher baseline than a blank ticket |
| 6. QA + validation | Manual QA against test data (2-5 days); test data often unrepresentative | Automated validation suite runs against synthetic data generated from client schema; AI agent identifies edge cases from historical integration failures | System: automated test runs. AI: edge case identification + synthetic data generation. Human: reviews failures and approves | If automated tests fail, agent generates a diagnostic summary for the engineer with likely root cause and suggested fix |
| 7. Client UAT | IM coordinates UAT via email; client unresponsive for days/weeks; scope creep | Client gets a self-service validation dashboard showing their data mapped in the platform; auto-generated comparison report: 'here's what we received vs. what's in the system' | System: dashboard + comparison report. AI: anomaly detection on mapped data. Human: client reviews and confirms | If client reports issues, agent routes to IM with specific discrepancy details and suggested resolution — not a vague 'something looks wrong' |
| 8. Deploy + monitor | Manual deploy coordination (1-2 days); monitoring relies on engineer attention; silent failures | Automated deploy on client sign-off; real-time monitoring with anomaly detection; auto-generated runbook for support | System: CI/CD + monitoring. AI: anomaly detection + runbook generation. Human: engineer reviews alerts; support handles known patterns | If anomaly detected, agent opens a ticket with context, impact assessment, and suggested action before the client notices |
| 9. Handoff to support | Tribal knowledge stays with IM/engineer; no runbook; support escalates everything | Auto-generated integration runbook + knowledge base entry created at deploy time; support agent has full context for first-ticket resolution | AI: runbook generation + KB entry. System: auto-routing. Human: support handles exceptions; engineer consulted only for novel issues | If support encounters a novel issue, agent drafts an escalation with full integration context so the engineer doesn't start from scratch |

What changes in the redesigned workflow

Estimated cycle time: 5-15 days for standard integrations (vs. 30-87 today). Custom integrations: 15-30 days.

The engineering queue bottleneck (Step 4) is eliminated for standard connectors — they deploy automatically.

The spec quality problem is solved at the source: AI generates the spec from structured intake data, not from an IM's interpretation of a call.

The handoff failure is prevented by auto-generated runbooks — support has full context from day one.

Humans are still in the loop at every high-judgment point: reviewing specs, approving deploys, handling exceptions, and making tradeoff calls.

### How to Apply This to Your Own Workflows

This example illustrates the level of depth required. Here's how to replicate it for any function:

- Pick one core workflow — not the whole function. 'Client onboarding' is too broad. 'Data integration during onboarding' is the right scope. You'll map multiple workflows, but one at a time.

- Walk the workflow physically — sit with the person who does the work. Watch them do it. Ask: what triggers you to start? What do you look at? What do you decide? Where do you go next? How long does each step take? Where do you get stuck?

- Name every system, handoff, and decision — if someone touches a tool, writes an email, opens a ticket, makes a judgment call, or waits for someone else — it's a step. If it's not in the map, it doesn't exist for planning purposes.

- Document failure modes honestly — where does it break? Where do people wait? Where does rework happen? These are your automation opportunities.

- Redesign with explicit boundaries — for each step, ask: should a human do this, should AI do this, or should a system automate this? Write the exception path — what happens when the AI/system can't handle it?

- Measure the delta — current cycle time vs. projected cycle time. Current error rate vs. projected. Current cost vs. projected. This is the impact math that makes the stack rank defensible.

The quality bar

If your workflow map looks like 5 boxes and 4 arrows, you haven't gone deep enough.

If your AI-native redesign doesn't have exception paths and human review points, you haven't been honest about what AI can and can't do.

If you can't estimate the cycle time delta, you don't have enough detail to make an investment decision.

The goal is not a perfect document. The goal is enough clarity to build the right thing.

# Appendix: Central Technical Enablement for an AI-Native Company

One of the most valuable outputs of the midpoint reviews and workflow diagrams is a picture of the common technical needs that surface across every functional plan. When multiple teams independently identify needs like database access, authentication, connector libraries, and shared data pipelines, that's the signal to build a central enablement layer — not let each team solve these problems independently.

This section describes what that enablement layer should look like, grounded in what emerges from the sprint process and informed by current best practices for enterprise AI infrastructure.

## How the Enablement Layer Emerges from the Sprint

The central enablement layer is not designed top-down. It is discovered bottom-up — through the sprint process itself:

- Functional plans surface needs independently: Sales needs Salesforce data. Finance needs ERP access. People needs the HRIS. Support needs the ticketing system. Separately, each is a one-off request. Together, it's a connector library.

- Midpoint reviews reveal the common denominator: the technical reviewers (CTO + top engineer) sit in every review session. They see the same needs surface in plan after plan — database tools, OAuth, data warehouse access, shared AI/LLM infrastructure. This is the pattern recognition that drives the enablement roadmap.

- Workflow diagrams make the dependencies concrete: when a functional leader draws the workflow and labels the systems touched, the CTO/top engineer can immediately see: this connector exists, this one doesn't, this one is needed by 4 teams. That's the prioritization input.

- The portfolio stack-rank sequences the build: the enablement layer doesn't build everything at once. It sequences based on which funded bets need which components first.

The key insight

The enablement layer exists to make the functional bets move faster — not as an independent initiative.

If you build enablement infrastructure that no funded bet consumes, you're building for the sake of building.

The sprint process ensures demand-driven prioritization: the functional plans create the demand; the enablement layer fulfills it.

## The Five Layers of Central AI Enablement

Based on current best practices and what typically surfaces from the sprint process, a central enablement platform includes five layers. Not all need to be built on day one — sequence based on funded bet dependencies.

### Layer 1: Shared Connector Library (Priority: Build First)

The most common and highest-leverage enablement investment. A growing library of pre-built, centrally maintained integrations to the core systems that appear in multiple functional plans.

| What it is | Pre-built, production-grade connectors to core enterprise systems — CRM, ERP, HRIS, data warehouse, ticketing, communication tools. Each connector handles authentication, rate limiting, error handling, and data normalization. |
| --- | --- |
| Why it matters | Without a shared library, every embedded engineer builds their own Salesforce integration, their own Snowflake connector, their own HRIS query. That's duplicated work, inconsistent patterns, and multiplied maintenance burden. |
| How to prioritize | Rank by coverage: which connectors are needed by the most funded bets? Build those first. A typical first wave includes CRM, data warehouse, core financial system, and identity/SSO. |
| Success metric | Connector reuse rate: % of integrations using shared connectors vs. building custom. Target: 70%+ by month 6. |

What 'connector' means in practice

A shared connector is not just an API wrapper. It includes: authentication (OAuth, API keys, SSO), rate limiting and retry logic, data normalization (consistent schema regardless of source), error handling and logging, and versioning so upstream API changes don't break every consumer.

The connector library is the single biggest anti-fragmentation investment. Build it early.

### Layer 2: Internal AI/LLM Platform

A standardized environment for building, deploying, and running AI-powered internal tools. The goal: functional teams focus on solving business problems, not on LLM infrastructure, prompt management, or deployment pipelines.

| What it is | A managed platform providing access to foundation models (LLMs), retrieval-augmented generation (RAG) capabilities, vector storage, prompt management, and a harness for non-engineers to build and test AI workflows without touching infrastructure code. |
| --- | --- |
| Core capabilities | LLM access with unified API (model-agnostic where possible); RAG pipeline with document ingestion, embedding, and retrieval; prompt versioning and evaluation; agent framework for multi-step workflows; observability: token usage, latency, cost tracking per team/use case. |
| Why model-agnostic matters | Enterprise AI is converging on a pattern where model choice is interchangeable for many use cases. Building on a single vendor's proprietary orchestration layer compounds lock-in. Architect the platform so models can be swapped without rewriting agents — this preserves optionality as capabilities and pricing evolve. |
| Success metric | Time to first working prototype: from engineer assignment to first functional AI workflow. Target: under 2 weeks. |

Key architecture decisions to make early:

- Model routing: which queries go to which model tier (fast/cheap vs. frontier/expensive)? Build this logic into the platform, not into each agent individually.

- Data boundaries: which data classifications are allowed in which model context windows? Enforce these at the platform level, not by policy alone.

- Cost visibility: teams need to see their own usage and cost. The platform must provide per-team, per-use-case cost tracking — this prevents shadow sprawl and informs portfolio decisions.

### Layer 3: Identity, Auth & Security Layer

Every AI workflow that touches enterprise data needs authentication, authorization, and audit logging. This is the layer most often rebuilt from scratch by individual teams — and the one with the highest cost of inconsistency.

| What it is | Centralized identity and access management for AI agents and workflows: SSO/OAuth integration, API key management, role-based access control (RBAC) for agent actions, and immutable audit logging of every agent action against enterprise systems. |
| --- | --- |
| Why centralize it | When each team builds their own auth for their own agent, you get: inconsistent security posture, no unified audit trail, and a proliferation of service accounts and API keys that are impossible to manage or revoke at scale. This is the single biggest enterprise AI security risk. |
| What to build | An 'Agent Identity' layer: each deployed agent gets a managed identity with explicit permissions (which systems it can read, which it can write, what actions it can take). Actions are logged. Permissions are revocable. Audit trails are queryable. |
| Success metric | % of deployed AI workflows using centralized auth vs. custom/ad-hoc auth. Target: 100% by month 4. |

### Layer 4: Data Access & Semantic Layer

AI workflows are only as good as the data they can access. A semantic data layer provides consistent, governed access to enterprise data — so agents and workflows get reliable, well-defined data without each team building bespoke data pipelines.

| What it is | A governed data access layer that provides: consistent data definitions across the organization (what 'revenue,' 'client,' 'active user' actually mean), pre-built data products for common analytical needs (client health, pipeline, utilization), and governed query access to the data warehouse / data lake with appropriate access controls. |
| --- | --- |
| Why it matters | Without a semantic layer, the same question — 'how many active clients do we have?' — produces different answers depending on which team's query runs. AI agents built on inconsistent data definitions produce inconsistent outputs. The semantic layer is the 'single source of truth' that all AI workflows consume. |
| What to build early | Start with the data products that the funded bets need most. Typical early priorities: client/account data, financial data (revenue, margin, pipeline), product usage/adoption data, and employee/org data. Don't boil the ocean — build what the top bets consume. |
| Success metric | % of AI workflows consuming data through the semantic layer vs. direct database queries. Also: number of conflicting data definitions resolved. |

### Layer 5: Observability, Governance & Agent Lifecycle

As AI workflows proliferate, the company needs a way to see what's running, how it's performing, what it costs, and when to retire it. This is the operational backbone that prevents the 'invisible entropy' problem at scale.

| What it is | A unified observability and governance layer for all AI workflows and agents: a registry of all deployed agents and automations (what they do, who owns them, what systems they touch), real-time monitoring (latency, error rate, cost, token usage), alert routing when agents behave unexpectedly, and lifecycle management (versioning, retirement, handoff procedures). |
| --- | --- |
| Why it matters | The Constraints Lab durability rules (owner, documentation, monitoring, retirement plan) are hard to enforce manually at scale. This layer automates that enforcement. It's the difference between 'we have a policy' and 'the system won't let you deploy without an owner and a monitoring config.' |
| What to build | An agent registry (the catalog of what's running), dashboards for usage and cost by team, automated alerts for error spikes or behavior drift, and lifecycle gates that enforce documentation and ownership before production deployment. |
| Success metric | % of agents in the registry with owners, documentation, and monitoring. Target: 100%. Also: mean time to detect and resolve agent failures. |

## Enablement Sequencing: What to Build When

| Horizon | Enablement Focus | Driven By |
| --- | --- | --- |
| Weeks 1-4 | Core infrastructure: LLM harness for non-technical users; first 3-5 shared connectors (highest coverage); centralized auth/identity scaffolding; basic agent registry | Funded Bet #1 dependencies + connectors that appear in 3+ plans |
| Weeks 5-8 | Expanding the library: next wave of shared connectors; RAG pipeline with document ingestion; semantic data layer for top 2-3 data products; cost tracking dashboards | Funded Bets #1-2 dependencies + common data needs surfaced in midpoint reviews |
| Months 3-6 | Platform maturity: full connector library for all funded bets; model routing (cheap vs. frontier); observability and alerting; lifecycle gates for deployment; self-service onboarding for new engineers | All funded bets + anticipating Bet #3 needs + reducing onboarding time |
| Months 6-12 | Industrialization: agent orchestration across functional boundaries; cross-system workflow automation; advanced governance (anomaly detection, drift monitoring); platform self-service for non-engineering teams | Scaling beyond initial bets + enabling next portfolio cycle + reducing central team bottleneck |

## Enablement OKRs

The enablement layer is a parallel workstream with its own success metrics — but those metrics are defined by how well it serves the functional bets, not by how much infrastructure it builds.

| OKR | Why It Matters | Target |
| --- | --- | --- |
| Time to onboard a new embedded engineer | Measures whether the platform actually reduces friction. If engineers spend their first 2 weeks on infrastructure setup, the platform isn't working. | < 1 week to first working prototype |
| Connector reuse rate | The anti-fragmentation metric. High reuse = engineers solving business problems. Low reuse = engineers rebuilding plumbing. | 70%+ of integrations use shared connectors by month 6 |
| Agent registry coverage | Can you see what's running? Without a registry, you're one engineer departure from orphan automations. | 100% of production agents registered with owners, docs, and monitoring |
| Mean time to detect agent failure | Silent failures are the biggest operational risk. If no one knows an agent broke until a user complains, observability has failed. | < 15 minutes for production agents |
| Cost per AI workflow | Visibility into economics. If you can't see costs by team and use case, you can't make portfolio decisions. | Per-team cost dashboards live by month 3 |
| Self-service success rate | The ultimate platform maturity test. Can a functional team spin up a new AI workflow without filing a ticket to the central team? | 50%+ of new workflows self-service by month 9 |

## Anti-Patterns to Avoid

Build it and they will come

Building enablement infrastructure before funded bets demand it. Every component should be pulled by a real use case, not pushed by a platform roadmap.

The fix: sequence the enablement layer strictly based on what the top funded bets need next.

The platform bottleneck

If every functional team's progress is blocked waiting on the central enablement team to build a connector, the enablement team has become the new bottleneck.

The fix: set aggressive SLAs for connector delivery. If the central team can't deliver a connector fast enough, the embedded engineer builds it — then the central team adopts and standardizes it.

Over-engineering the platform

Building a perfect, fully-governed, enterprise-grade platform before a single agent is in production. Perfection is the enemy of learning.

The fix: start with the minimum viable platform that lets Bet #1 move. Harden iteratively based on what breaks in production.

Vendor capture at the orchestration layer

Building deeply on a single vendor's proprietary agent orchestration framework compounds lock-in at every layer. If your agents, connectors, and data flows are all vendor-specific, switching costs grow faster than you realize.

The fix: architect for interoperability. Use open standards (e.g., MCP for agent-to-tool connections) where possible. Keep model choice swappable. Build your connector library as vendor-neutral plumbing.